# Statement of Work - Functional Safety Software Development and CAN Database Optimization

Template for United States of America
Fixed-Price Standalone SOW

July 14, 2025

Presented By:

Praveen Manager

Technical Manager

7301 Parkway Drive, Hanover, MD 21076

+1 9234567892

pravenn@cfeynman.com

Revision Table

| Revision | Date | Description of Change |
| --- | --- | --- |
| 1.0 | XXXXX | Initial Release |

Confidentiality Statement

This document contains information that is privileged, confidential, and otherwise protected from disclosure to anyone other than intended recipient(s). As a result, this information should not be disclosed, duplicated or used for any other purpose than to evaluate Actalent. On signing the contract as a result of the process initialized by submission of this document, any right to disclose, duplicate or use the data contained within this document will be to the extent provided in the resulting agreement

Table of Contents

1	Introduction	2

2	Executive Summary	2

3	Scope of Work	2

3.1	Project Requirements	3

3.2	Assumptions	3

3.3	Methodology or Approach	3

3.4	Acceptance Criteria	4

4	Assets/Information Required	4

5	Governance and Review	5

6	Out of Scope	5

7	Deliverables	6

8	Project Schedule	6

9	Proposed Team and Organization	7

10	Data Retention	7

11	Risk Management	8

12	Change Management	8

13	Project Pricing	8

14	Project Assumptions and Client Responsibilities	9

15	Contact Information	9

Table of Exhibits

Exhibit A – Change Order	27

# Introduction

This Statement of Work (SOW) dated the 14th day of July, 2025 (the "Effective Date") is made and entered into by and between Danfoss, a New Jersey corporation, having a place of business at [Enter Client address here] (the "Client") and CFeynmanCompany Services, LLC, a Maryland limited liability company, having its principal place of business at 7301 Parkway Drive, Hanover, MD 21076 ("CFeynmanCompany"); individually referenced hereafter as "Party" and collectively referenced hereafter as the "Parties".

# Executive Summary

Danfoss is currently developing advanced firmware for a new inverter module and faces critical challenges in two key areas. First, the client needs to complete approximately 110 safety software requirements and perform rigorous ISO 26262 verification and validation (V&V), which is consuming significant resources from their core development team. Second, their DYNO test environment is experiencing critical failures due to CAN DBC file issues, creating a bottleneck that is blocking their testing progress and overall project timeline.

CFeynmanCompany proposes a comprehensive solution utilizing our proven blended-shore delivery model. Our India Design Center will handle the bulk of the V&V work and safety requirement implementation, while our US-based functional safety consultant will provide high-value guidance and oversight. The engagement will be structured as a Time & Materials project delivered through a three-phase approach: a paid Discovery phase to analyze and define the actual scope, followed by two implementation phases. This structure will ensure flexibility for the client while providing the necessary de-risking for both parties.

The project will be managed through close coordination between CFeynmanCompany's technical team and Danfoss stakeholders, with regular milestone reviews and governance processes to ensure quality and progress. Our team will act as an extended part of the Danfoss development organization, providing specialized functional safety expertise while working seamlessly with their existing processes and tools.

# Scope of Work

This section lists the project requirements that must be met and describes these requirements as CFeynmanCompany understands them. The project is structured in three phases to provide maximum flexibility and risk mitigation for both parties.

## Project Requirements

This subsection lists all the Client project requirements as understood by CFeynmanCompany:

Implementation of approximately 110 remaining safety software requirements in accordance with ISO 26262-6 standard

Code refactoring to align existing codebase with Danfoss specified TSC (Technical Safety Concept) Architecture

Creation of comprehensive architectural and detailed design documents for safety lifecycle evidence

Development and execution of unit tests to achieve required code coverage metrics (Statement, Branch, MC/DC)

Performance of bench-level integration and requirement-based testing on physical hardware

Execution of remote HIL testing including fault insertion tests to validate safety mechanism effectiveness

Investigation and resolution of critical DYNO test environment data acquisition failures

Consolidation and optimization of multiple existing DBC files into master DBCs compatible with DYNO data acquisition module

## Assumptions

This subsection describes assumptions identified for the completion of this project:

The actual scope of code refactoring will be determined during Phase 1 Discovery activities

Danfoss will provide timely access to subject matter experts for clarifications and reviews

All required development tools and licenses will be provided by the client or costs will be passed through

Hardware kits and HIL systems will be available and properly configured for testing activities

The root cause of DBC file issues will be identifiable through analysis during Phase 1

Danfoss development processes and quality standards will be clearly documented and accessible

## Methodology or Approach

CFeynmanCompany will implement a three-phase approach designed to mitigate risk while providing maximum value to Danfoss:

Phase 1: Paid Discovery and Gap Analysis (Time & Materials)

This critical de-risking phase will involve comprehensive analysis of the existing codebase, identification of the actual scope of refactoring required, and immediate resolution of the DBC file issues as a quick win. The team will conduct detailed code review, architecture analysis, and requirements mapping to define the precise scope for subsequent phases.

Phase 2: Safety Requirements Implementation (Indicative Scope)

Based on Phase 1 findings, this phase will focus on implementing the remaining safety requirements, code refactoring, and creation of design documentation. The scope and timeline for this phase will be formally defined through a Change Order based on Phase 1 deliverables.

Phase 3: Verification and Validation (Indicative Scope)

This phase will encompass comprehensive V&V activities including unit testing, integration testing, HIL testing, and fault insertion validation. Like Phase 2, the detailed scope will be defined based on Phase 1 analysis and formally documented through Change Order processes.

## Acceptance Criteria

This section identifies and describes the conditions that must be met for acceptance by the Client:

All deliverables must pass Danfoss quality management review processes and technical standards

Code deliverables must achieve specified coverage metrics (Statement, Branch, MC/DC) as defined in the safety plan

DBC files must demonstrate successful data acquisition in the DYNO test environment

Software design documents must provide adequate evidence for ISO 26262 safety lifecycle compliance

All test results must meet the acceptance criteria defined in the respective test plans

Deliverables will be subject to a 15-day review period; if no written objections are received within this timeframe, deliverables will be deemed accepted

HIL test results must demonstrate successful fault insertion and safety mechanism validation

# Assets/Information Required

This section identifies and describes the required assets, information, and tools required from the Client to complete the project:

Hardware: Two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at client expense, including all necessary cables and documentation

Remote Access: Uninterrupted access to a stable, pre-configured HIL system with necessary permissions for testing and fault insertion

Configured Development Environment: A laptop pre-configured with all development tools, compilers, and access credentials ready for immediate use

Technical Documentation: Complete TSC (Technical Safety Concept), existing codebase, safety requirements specifications, and current DBC files

Subject Matter Expert Access: Timely availability of Danfoss technical experts for clarifications, reviews, and technical discussions

Development Tools: Access to or provision of Vector Cast, PC-LINT, and other required development and testing tools

Quality Standards Documentation: Complete documentation of Danfoss development processes, coding standards, and quality requirements

# Governance and Review

This section addresses the governance and review applied towards the completion of this project including regular status meetings, milestone reviews, and quality gates:

Weekly status meetings between CFeynmanCompany project team and Danfoss stakeholders

Phase gate reviews at the completion of each project phase with formal go/no-go decisions

Deliverable reviews with 15-day review cycle and deemed acceptance clause

Budget monitoring with Change Order process triggered at 80% budget utilization

Escalation procedures for technical issues and project risks

Quality gate reviews for all safety-critical deliverables before client submission

# Out of Scope

This section states the agreed upon requirements and/or items not included in the Scope of Work:

Development environment setup and tool configuration (client responsibility)

Hardware procurement and shipping arrangements beyond the specified kits

Long-term maintenance or support beyond the project completion

Modification of Danfoss existing development processes or quality standards

Training of Danfoss personnel on delivered software or processes

Warranty or product liability for prototype hardware or software beyond professional services

Integration with other Danfoss systems not directly related to the inverter module

Compliance certification or regulatory approval processes

# Deliverables

This SOW describes the support needs relating to the project in terms of the following deliverables:

Phase 1 Gap Analysis Report - Electronic submission via secure file transfer, including detailed findings and scope recommendations for subsequent phases

Consolidated DBC File(s) - Electronic delivery via client's version control system, fully functional and optimized for DYNO data acquisition

Software Design Document - Electronic submission, comprehensive documentation detailing high-level and low-level design of safety software

Refactored Safety Software Source Code - Electronic delivery via client's version control system, complete and tested code for implemented safety functions

Software Verification & Validation Report - Electronic submission, detailed report containing static analysis, unit test results, integration test results, and HIL testing validation

Unit Test Suite and Coverage Reports - Electronic delivery, complete test suite with achieved coverage metrics documentation

HIL Test Results and Fault Insertion Validation - Electronic submission, comprehensive test results demonstrating safety mechanism effectiveness

# Project Schedule

This section describes the project schedule, including the start date and estimated completion date.

Project Start Date

Target project kick-off: September 4, 2025, subject to completion of contract execution and availability of required client assets.

Phase Schedule

Phase 1 (Discovery and Gap Analysis): 4-6 weeks from project start

Phase 2 (Safety Requirements Implementation): Duration to be determined based on Phase 1 findings

Phase 3 (Verification and Validation): Duration to be determined based on Phase 1 findings

Estimated Completion Date

Total project duration is estimated at 16-20 weeks, with completion targeted for January 2026. Final timeline will be established upon completion of Phase 1 analysis.

# Proposed Team and Organization

CFeynmanCompany will deploy a blended-shore team model leveraging our India Design Center for core development activities and US-based consultants for functional safety expertise and client coordination.

| Role | Classification | Location | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Core | US | Overall project coordination, client communication, schedule management |
| Functional Safety Lead | Core | US | ISO 26262 compliance guidance, safety architecture review, V&V oversight |
| Senior Embedded Engineer | Core | India | Code implementation, refactoring, unit testing |
| Software Test Engineer | Core | India | Test development, HIL testing, coverage analysis |
| CAN/DBC Specialist | Support | India | DBC file analysis and optimization |
| Technical Manager | Support | India | Team coordination, technical guidance, quality assurance |

RASCI Matrix

Key: R = Responsible, A = Accountable, S = Supporting, C = Consulted, I = Informed

| Task | Project Manager | Functional Safety Lead | Senior Embedded Engineer | Software Test Engineer | CAN/DBC Specialist | Technical Manager |
| --- | --- | --- | --- | --- | --- | --- |
| Project Planning | A | C | R | S | I | S |
| Tracking Effort | A | I | S | S | I | C |
| Code Implementation | S | C | A | S | R | I |
| Reviewing Deliverables | C | A | C | R | S | S |
| Client Communication | A | S | I | I | I | I |
| Quality Assurance | S | C | S | S | S | A |
| HIL Testing | S | C | S | A | R | S |

# Data Retention

Project data including source code, documentation, test results, and communications will be retained by CFeynmanCompany in secure systems for the duration of the project and 24 months following project completion. All project artifacts will be stored in accordance with ISO 27001 security standards. Danfoss will have access to all project data throughout the engagement. Upon project completion, all deliverables and associated data will be transferred to Danfoss systems as specified. CFeynmanCompany will delete all retained data 24 months after project completion unless otherwise agreed in writing.

# Risk Management

The following risk management plan identifies potential risks, assigns ownership, and defines mitigation strategies:

| Risk | Probability | Owner | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- | --- |
| Scope Creep | High | CFeynmanCompany PM | Three-phase approach with formal scope definition | Change Order process at 80% budget |
| Hardware Availability | Medium | Danfoss | Early procurement and shipping | Backup hardware kits |
| Tool Licensing | Medium | Danfoss | Early identification of tool requirements | Pass-through cost model |
| HIL System Access | Medium | Danfoss | Stable system configuration | Backup testing approach |
| Resource Availability | Low | CFeynmanCompany | Dedicated team allocation | Cross-training and backup resources |

# Change Management

Changes to project scope, schedule, or budget will be managed through a formal Change Order process. When project costs reach 80% of the approved budget, CFeynmanCompany will initiate change management discussions with Danfoss. All scope changes beyond the original SOW will require written approval from both parties before implementation. The Change Order process includes impact assessment, cost estimation, schedule adjustment, and formal approval workflow.

# Project Pricing

This project will be delivered on a Time & Materials basis to provide maximum flexibility for scope adjustments. The pricing structure reflects the blended-shore delivery model and includes all labor costs. Tool licenses and hardware costs will be passed through at cost.

| Job Title | Description | Weekly Fee (USD) |
| --- | --- | --- |
| Project Manager | Overall project coordination and client communication | $2,400 |
| Functional Safety Lead | ISO 26262 expertise and safety architecture guidance | $2,800 |
| Senior Embedded Engineer | Code implementation, refactoring, and unit testing | $1,600 |
| Software Test Engineer | Test development and validation activities | $1,400 |
| CAN/DBC Specialist | CAN database optimization and analysis | $1,200 |
| Technical Manager | Team coordination and quality assurance | $1,800 |

Additional Pricing

Tool licenses including Vector Cast, PC-LINT, and other required development tools are the client's financial responsibility. CFeynmanCompany can procure these tools on behalf of Danfoss, with costs passed through at actual cost plus 5% administrative fee.

Estimated Budget

Phase 1 estimated budget: $65,000 - $80,000. Total project estimated budget: $280,000 - $350,000 (subject to refinement based on Phase 1 findings). Change Order process will be triggered at 80% budget utilization.

# Project Assumptions and Client Responsibilities

The following assumptions and client responsibilities are critical to project success:

Project Assumptions

Danfoss subject matter experts will be available within 24 hours for technical clarifications

All required documentation and specifications will be provided in English

HIL system will be available and stable for remote access throughout the project

Existing codebase is in a buildable state with documented build procedures

Safety requirements are clearly defined and traceable to system requirements

Client Responsibilities

Provide two complete hardware kits with harnesses shipped to India Design Center

Ensure uninterrupted access to HIL system with proper configuration

Provide pre-configured laptop with all development tools and access credentials

Make subject matter experts available for timely reviews and clarifications

Provide or fund all required tool licenses (Vector Cast, PC-LINT, etc.)

Conduct timely reviews of deliverables within the 15-day acceptance window

Provide comprehensive technical documentation and safety requirements

# Contact Information

| Name | Role | Phone | Email |
| --- | --- | --- | --- |
| Praveen Manager | Technical Manager | +1 9234567892 | pravenn@cfeynman.com |
| TBD | Project Manager | TBD | TBD |
| Peter Parker | Head of Procurement | +1 9234567892 | spiderman@danfoss.com |
| TBD | Technical Lead | TBD | TBD |