# Statement of Work

Template for United States of America
Fixed-Price Standalone SOW

14/Jul/2025

Presented By:

Praveen

Technical Manager

7301 Parkway Drive, Hanover, MD 21076

+1 9234567892

pravenn@cfeynman.com

Revision Table

| Revision | Date | Description |
|----------|------|-------------|
| 1.0 | 14/Jul/2025 | Initial Draft |

| Revision | Date | Description of Change |
| --- | --- | --- |
| 1.0 | XXXXX | Initial Release |

Confidentiality Statement

This document contains information that is privileged, confidential, and otherwise protected from disclosure to anyone other than intended recipient(s). As a result, this information should not be disclosed, duplicated or used for any other purpose than to evaluate Actalent. On signing the contract as a result of the process initialized by submission of this document, any right to disclose, duplicate or use the data contained within this document will be to the extent provided in the resulting agreement

Table of Contents

No table of contents entries found.

Table of Exhibits

Exhibit A – Change Order	27

# Introduction

This Statement of Work (SOW) dated the 14th day of July, 2025 (the "Effective Date") is made and entered into by and between Danfoss, a corporation having a place of business at New Jersey (the "Client") and CFeynmanCompany Services, LLC, a Maryland limited liability company, having its principal place of business at 7301 Parkway Drive, Hanover, MD 21076 ("CFeynmanCompany"); individually referenced hereafter as "Party" and collectively referenced hereafter as the "Parties".

# Executive Summary

Danfoss is developing advanced firmware for a safety-critical inverter module and requires expert support to complete the implementation, verification, and validation (V&V) of approximately 110 safety software requirements in compliance with ISO 26262 standards. Additionally, Danfoss is experiencing critical data acquisition issues in their DYNO test environment due to CAN database (DBC) file inconsistencies that are blocking their testing progress.

CFeynmanCompany proposes a three-phase Time & Materials engagement utilizing our proven blended-shore delivery model. Our India Design Center will handle the bulk of the V&V work and software implementation, while our US-based functional safety consultant will provide high-value ISO 26262 guidance and oversight. This approach offers Danfoss the flexibility needed for a project with evolving requirements while ensuring compliance with the highest safety standards.

The engagement will be managed through structured phases with clear milestone reviews and deliverable acceptance criteria. Phase 1 will serve as a paid discovery phase to analyze existing code, define the actual scope of work, and deliver an immediate DBC fix as a quick win. This de-risking approach ensures proper project scoping before proceeding to the full implementation phases, with our team acting as an extension of Danfoss's internal development team.

# Scope of Work

This section lists the project requirements that must be met and describes these requirements as CFeynmanCompany understands them. The scope is structured in three phases to manage risk and ensure proper project definition before full-scale implementation.

## Project Requirements

The Client project requirements as understood by CFeynmanCompany include:

Implementation of approximately 110 remaining safety software requirements for the Safety CPU in accordance with ISO 26262-6 standard

Code refactoring of existing codebase to align with Danfoss specified TSC (Technical Safety Concept) Architecture

Resolution of critical data acquisition bottleneck in DYNO test environment related to CAN database translation issues

Creation of comprehensive design documentation serving as evidence for safety lifecycle compliance

Development and execution of unit tests to achieve required code coverage metrics (Statement, Branch, MC/DC)

Performance of bench-level integration and requirement-based testing

Execution of HIL testing including fault insertion tests to validate safety mechanism effectiveness

Consolidation and optimization of multiple existing DBC files into master DBC(s) compatible with DYNO data acquisition module

## Assumptions

Client will provide two complete hardware kits with harnesses shipped to CFeynmanCompany India Design Center at Client's expense

Client will provide uninterrupted remote access to stable, pre-configured HIL system

Client will provide a configured laptop ready for development work to minimize setup time

Client's subject matter experts will be available for timely clarifications and reviews

Existing codebase and documentation will be made available for analysis during Phase 1

The actual scope of code refactoring will be determined during the paid discovery phase

Tool licenses (Vector Cast, PC-LINT, etc.) costs will be passed through to Client or Client will provide direct access

Project timeline assumes no significant delays in Client-provided dependencies

## Methodology or Approach

CFeynmanCompany will implement a three-phase approach utilizing our proven blended-shore delivery model:

Phase 1: Paid Discovery and Gap Analysis (4-6 weeks)

Comprehensive analysis of existing codebase and architecture

Root cause analysis of DBC file issues and immediate fix implementation

Definition of actual scope for safety requirements implementation

Gap analysis of current state vs. ISO 26262 compliance requirements

Detailed project plan and effort estimates for Phases 2 and 3

Quick win delivery: Functional DBC file for DYNO testing

Phase 2: Safety Requirements Implementation (Indicative: 12-16 weeks)

Implementation of identified safety software requirements

Code refactoring aligned with TSC architecture

Development of comprehensive design documentation

Unit test development and execution for code coverage compliance

Static code analysis and MISRA compliance verification

Phase 3: Verification and Validation (Indicative: 8-12 weeks)

Bench-level integration and requirement-based testing

HIL testing execution including fault insertion validation

Comprehensive V&V report generation

Final safety compliance documentation

Knowledge transfer and project closure

Note: Phases 2 and 3 scope and timeline are indicative only and will be formally defined based on the findings and recommendations from Phase 1. Any scope changes will be managed through the formal Change Order process.

## Acceptance Criteria

The following conditions must be met for formal acceptance by the Client:

All deliverables meet the technical specifications and quality standards defined in this SOW

Software implementation passes all unit tests with required code coverage metrics (Statement, Branch, MC/DC)

Design documentation is complete and compliant with ISO 26262 standards

HIL testing demonstrates successful validation of safety mechanisms through fault insertion tests

DBC files enable successful data acquisition in DYNO test environment

All deliverables are subject to Client review and will be deemed accepted if no written objections are received within 15 calendar days of delivery

Acceptance procedures will follow the formal review and sign-off process outlined in the project governance section

# Assets/Information Required

The following assets, information, and tools are required from the Client to enable successful completion of the project:

Hardware: Two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at Client's expense before project start

Remote Access: Uninterrupted access to stable, pre-configured HIL system with necessary permissions and connectivity

Development Environment: One configured laptop ready for development work with all necessary software tools and licenses pre-installed

Documentation: Complete existing codebase, architecture documents, TSC specifications, safety requirements, and current DBC files

Tool Licenses: Client to provide or fund licenses for Vector Cast, PC-LINT, and other required development/testing tools

Subject Matter Expert Access: Timely availability of Client technical experts for clarifications, reviews, and decision-making

Test Environment Access: Credentials and access to DYNO test system for validation and troubleshooting

Escalation Process: Defined escalation path for issue resolution and decision-making to prevent project delays

# Governance and Review

This section addresses the governance and review processes applied towards the completion of this project including status reporting, milestone reviews, and quality gates.

Weekly status meetings between CFeynmanCompany Project Manager and Client stakeholders

Bi-weekly milestone reviews at phase boundaries with formal deliverable presentations

15-day deliverable review cycle with deemed acceptance if no written feedback is provided

Monthly project steering committee reviews for budget tracking and scope management

Escalation procedures for technical issues requiring Client SME input within 48 hours

Quality gates at the end of each phase requiring formal Client approval before proceeding

Change Order process triggered at 80% of phase budget burn to manage scope and cost variations

Final project review and knowledge transfer session upon completion

# Out of Scope

The following items are explicitly NOT included in this engagement and would require a separate Change Order if needed:

Hardware design or modification of the inverter module

Development of non-safety related firmware functions

Production software deployment and manufacturing support

Long-term maintenance or support beyond project completion

Training of Client personnel beyond knowledge transfer sessions

Certification body interactions or safety case preparation beyond documentation

Development of additional test equipment or test automation frameworks

Integration with Client's broader product development lifecycle tools

Modification of Client's existing development processes or methodologies

# Deliverables

The following deliverables will be provided throughout the project phases:

Phase 1 Deliverables

Fixed and optimized DBC file(s) for DYNO data acquisition system

Comprehensive gap analysis report detailing current state vs. ISO 26262 requirements

Detailed project plan and scope definition for Phases 2 and 3

Risk assessment and mitigation strategy document

Effort estimation and resource allocation plan for remaining phases

Phase 2 Deliverables (Indicative)

Refactored safety software source code compliant with TSC architecture

Comprehensive software design document (high-level and detailed design)

Unit test suite with achieved code coverage metrics

Static code analysis report demonstrating MISRA compliance

Software integration and build documentation

Phase 3 Deliverables (Indicative)

Complete software verification and validation report

HIL testing results including fault insertion validation

Bench testing results and integration test reports

Final safety compliance documentation package

Knowledge transfer documentation and training materials

All deliverables will be provided electronically via secure file transfer. Hard copy deliverables will be shipped to: Danfoss, New Jersey (specific shipping address to be provided by Client).

# Project Schedule

Project Start Date: September 4, 2025

Phase 1 Completion: October 16, 2025 (6 weeks)

Phase 2 Completion: February 3, 2026 (16 weeks - indicative)

Phase 3 Completion: April 28, 2026 (12 weeks - indicative)

Estimated Total Project Duration: 34 weeks

Note: Phases 2 and 3 schedules are indicative and will be finalized based on Phase 1 findings

# Proposed Team and Organization

CFeynmanCompany will provide a dedicated team utilizing our proven blended-shore delivery model with both US-based and India Design Center resources.

Roles and Responsibilities

| Role | Classification | Location | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Core | US | Overall project coordination, client communication, risk management |
| Functional Safety Lead | Core | US | ISO 26262 compliance oversight, safety architecture guidance |
| Senior Embedded Engineer | Core | India | Software implementation, code refactoring, technical leadership |
| Embedded Software Engineers (2) | Core | India | Safety requirements implementation, unit testing |
| V&V Engineer | Core | India | Test development, HIL testing, validation reporting |
| CAN/Automotive Engineer | Support | India | DBC optimization, automotive protocols expertise |
| Technical Writer | Support | India | Documentation development, compliance reporting |

RASCI Matrix

| Task | Project Manager | Safety Lead | Sr. Embedded Eng | Embedded Eng | V&V Engineer | CAN Engineer | Tech Writer |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | A | R | C | I | I | I | I |
| Safety Requirements Implementation | I | A | R | R | C | I | S |
| Code Refactoring | I | C | A | R | I | I | I |
| Unit Testing | I | C | C | R | A | I | I |
| HIL Testing | I | A | S | I | R | C | I |
| DBC Optimization | I | C | S | I | I | A | R |
| Documentation | C | C | S | S | S | I | A |
| Client Communication | A | R | I | I | I | I | S |

# Data Retention

CFeynmanCompany will retain project data according to the following guidelines:

All project deliverables and working files will be securely stored for a minimum of 5 years

Client data will be handled in accordance with applicable data protection regulations

Access to project data will be restricted to authorized team members only

Data backup and recovery procedures will be maintained throughout the project lifecycle

Upon project completion, all Client proprietary information will be returned or securely destroyed as requested

CFeynmanCompany may retain anonymized project insights for internal process improvement purposes

Data retention practices comply with ISO 27001 security standards

# Risk Management

The following risk management approach will be implemented:

| Risk | Probability | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- |
| Scope Creep | High | Three-phase approach with paid discovery to define actual scope | Change Order process at 80% budget burn |
| Client Dependency Delays | Medium | Clear definition of required assets and escalation procedures | Built-in buffer time and parallel work streams |
| Technical Complexity | Medium | Senior team with proven ISO 26262 expertise | Regular technical reviews and safety oversight |
| Tool License Costs | Low | Pass-through pricing model for all tool costs | Client responsibility clearly defined in SOW |
| Remote Work Challenges | Low | Established remote collaboration processes | Dedicated communication protocols and tools |

# Change Management

Changes to the project scope, timeline, or budget will be managed through the following process:

Change requests must be submitted in writing with detailed scope and impact analysis

CFeynmanCompany will provide effort estimates and timeline impacts within 5 business days

All changes require formal approval from both parties before implementation

Change Order process will be triggered automatically at 80% of phase budget consumption

Emergency changes may be implemented with verbal approval followed by written confirmation within 24 hours

All approved changes will be documented and incorporated into project tracking

Phase 2 and 3 scope changes will be managed through formal SOW amendments based on Phase 1 findings

# Project Pricing

This engagement is structured as a Time & Materials project to provide flexibility for evolving requirements. The following pricing structure applies:

Pricing Table

| Job Title | Description | Hourly Rate |
| --- | --- | --- |
| Project Manager | Overall project management and client coordination | $180/hour |
| Functional Safety Lead | ISO 26262 compliance and safety architecture oversight | $220/hour |
| Senior Embedded Engineer | Technical leadership and complex implementation | $160/hour |
| Embedded Software Engineer | Software development and testing | $140/hour |
| V&V Engineer | Verification and validation activities | $150/hour |
| CAN/Automotive Engineer | Automotive protocols and DBC optimization | $145/hour |
| Technical Writer | Documentation and compliance reporting | $120/hour |

Milestone Payment Schedule

| Milestone/Deliverable | Due Date | Estimated Amount |
| --- | --- | --- |
| Phase 1 Completion | October 16, 2025 | $85,000 |
| Phase 2 - 50% Completion | December 19, 2025 | $120,000 |
| Phase 2 Completion | February 3, 2026 | $120,000 |
| Phase 3 - 50% Completion | March 17, 2026 | $90,000 |
| Phase 3 Completion | April 28, 2026 | $90,000 |

Additional Pricing

Tool Licenses: Vector Cast, PC-LINT, and other required development tools are pass-through costs at actual vendor pricing

Hardware Shipping: Client responsibility for shipping hardware kits to India Design Center

Travel Expenses: Any required on-site visits will be billed at cost plus 10% administrative fee

Estimated Total Project Cost: $505,000 (indicative only, actual cost based on time and materials)

Change Order Trigger: Process initiated at 80% of estimated phase budget consumption

# Project Assumptions and Client Responsibilities

The following assumptions and client responsibilities are critical for project success:

Project Assumptions

Existing codebase is reasonably well-structured and documented

Client will provide timely responses to technical questions and review requests

HIL system will be stable and available for remote testing throughout the project

No major changes to safety requirements or architecture during implementation

Client SMEs will be available within agreed response timeframes

All necessary legal agreements and NDAs are in place before project start

Client Responsibilities

Provide complete hardware kits with harnesses shipped to CFeynmanCompany India Design Center

Ensure uninterrupted remote access to HIL system with proper network connectivity

Supply configured development laptop with all necessary software pre-installed

Provide or fund all required tool licenses (Vector Cast, PC-LINT, etc.)

Make subject matter experts available for timely clarifications and reviews

Maintain escalation procedures for quick resolution of technical and contractual issues

Provide complete and current project documentation including existing code and specifications

Approve deliverables within 15 calendar days or provide detailed written feedback

# Contact Information

| Name | Role | Phone | Email |
| --- | --- | --- | --- |
| Praveen | Technical Manager | +1 9234567892 | pravenn@cfeynman.com |
| Enter Name | Project Manager | Enter Phone | Enter Email |
| Peter Parker | Head of Procurement | +1 9234567892 | spiderman@danfoss.com |
| Enter Name | Technical Lead | Enter Phone | Enter Email |

# Terms and Conditions

This SOW is governed by the standard CFeynmanCompany Terms and Conditions. The following specific terms apply to this engagement:

15-day deemed acceptance clause applies to all deliverables

Time & Materials pricing model with Change Order process at 80% budget burn

Tool license costs are pass-through expenses at actual vendor rates

Prototype liability limitation: prototypes are for testing only, not production use

Data retention period of 5 years with secure handling procedures

Standard intellectual property and confidentiality provisions apply

T&C Exceptions

| T&C Item Number | Change | Approved (Y/N) |
| --- | --- | --- |
| TBD | TBD | TBD |

Authorization

| Party | Name | Title | Date |
| --- | --- | --- | --- |
| Client | Enter Name | Enter Title | Enter Date |
| CFeynmanCompany | Enter Name | Enter Title | Enter Date |

# Exhibits

## Exhibit A – Change Order

Change Order Number: [Enter Number]

Date: [Enter Date]

Project Name: Danfoss Functional Safety Software Development

Change Description

| Description of Change | Reason for Change | Impact on Project |
| --- | --- | --- |
| Enter Description | Enter Reason | Enter Impact |

Cost Impact

| Item | Hours | Rate | Amount |
| --- | --- | --- | --- |
| Additional Hours | Enter Value | Enter Rate | Enter Amount |
| Reduced Hours | Enter Value | Enter Rate | Enter Amount |
| Net Cost Impact |  |  | Enter Total |

Schedule Impact

| Item | Date/Duration |
| --- | --- |
| Original Completion Date | Enter Date |
| Revised Completion Date | Enter Date |
| Schedule Impact | Enter Days |

Approval

| Party | Name | Title | Date |
| --- | --- | --- | --- |
| Client | Enter Name | Enter Title | Enter Date |
| CFeynmanCompany | Enter Name | Enter Title | Enter Date |