# Statement of Work

Template for United States of America
Fixed-Price Standalone SOW

15/Jul/2025

Presented By:

Praveen

Manager

7301 Parkway Drive, Hanover, MD 21076

+1 9234567892

praveen@cfeynman.com

Revision Table

| Revision | Date | Description of Change |
| --- | --- | --- |
| 1.0 | XXXXX | Initial Release |

Confidentiality Statement

This document contains information that is privileged, confidential, and otherwise protected from disclosure to anyone other than intended recipient(s). As a result, this information should not be disclosed, duplicated or used for any other purpose than to evaluate Actalent. On signing the contract as a result of the process initialized by submission of this document, any right to disclose, duplicate or use the data contained within this document will be to the extent provided in the resulting agreement

Table of Contents

1	Introduction	2

2	Executive Summary	2

3	Scope of Work	3

3.1	Project Requirements	3

3.2	Assumptions	3

3.3	Methodology or Approach	4

3.4	Acceptance Criteria	4

4	Assets/Information Required	5

5	Governance and Review	5

6	Out of Scope	5

7	Deliverables	6

8	Project Schedule	6

9	Proposed Team and Organization	7

10	Data Retention	8

11	Risk Management	8

12	Change Management	8

13	Project Pricing	9

14	Project Assumptions and Client Responsibilities	9

15	Contact Information	10

Table of Exhibits

Exhibit A – Change Order	27

| Revision | Date | Description | Author |
| --- | --- | --- | --- |
| 1.0 | 15/Jul/2025 | Initial Draft | Praveen |

# Introduction

This Statement of Work (SOW) dated the 15th day of July, 2025 (the "Effective Date") is made and entered into by and between Danfoss, a corporation, having a place of business at New Jersey ("Client") and CFeynmanCompany Services, LLC, a Maryland limited liability company, having its principal place of business at 7301 Parkway Drive, Hanover, MD 21076 ("CFeynmanCompany"); individually referenced hereafter as "Party" and collectively referenced hereafter as the "Parties".

# Executive Summary

Danfoss is developing advanced firmware for a safety-critical inverter module and requires specialized support in two critical areas: implementation, verification, and validation of approximately 110 safety software requirements in compliance with ISO 26262-6 standards, and resolution of critical data acquisition issues in their DYNO test environment caused by CAN database file inconsistencies. The client needs to complete rigorous functional safety V&V processes while addressing a critical bottleneck that is blocking their testing progress.

CFeynmanCompany proposes a three-phase Time & Materials approach leveraging our blended-shore delivery model. Our India Design Center will handle the bulk of the V&V work under guidance from our US-based functional safety consultant. The engagement will begin with a paid Discovery phase to de-risk the project by analyzing the existing codebase, defining the actual scope of refactoring required, and delivering an immediate resolution to the DBC file issues as a quick win. This will be followed by indicative implementation phases for the remaining safety requirements and comprehensive V&V activities.

The project will be managed through a collaborative extended-team model with clear governance processes, milestone reviews, and a formal change management process triggered at 80% budget utilization. Our US consultant will provide high-value functional safety guidance and oversight, while our India team delivers cost-effective implementation and testing services. This approach ensures both technical excellence and budget optimization for Danfoss while maintaining strict ISO 26262 compliance throughout the engagement.

# Scope of Work

This section lists the project requirements that must be met and describes these requirements as CFeynmanCompany understands them. The scope is structured in three phases to manage risk and ensure clear deliverables at each stage.

## Project Requirements

The Client project requirements as understood by CFeynmanCompany include:

Implementation of approximately 110 remaining safety software requirements in compliance with ISO 26262-6 standard

Code refactoring of existing safety CPU firmware to align with Danfoss Technical Safety Concept (TSC) Architecture

Resolution of CAN database (DBC) file issues causing data acquisition failures in DYNO test environment

Development of comprehensive architectural and detailed design documentation

Creation and execution of unit tests to achieve required code coverage metrics (Statement, Branch, MC/DC)

Performance of bench-level integration and requirement-based testing

Execution of HIL testing including fault insertion tests to validate safety mechanism effectiveness

Static code analysis for MISRA compliance

Production of comprehensive Software Verification & Validation Report

## Assumptions

The following assumptions have been identified for the completion of this project:

Danfoss will provide two complete hardware kits with harnesses shipped to CFeynmanCompany India Design Center at Client expense

Client will provide uninterrupted remote access to a stable, pre-configured HIL system

A configured development laptop will be provided by the Client, ready for immediate use

Danfoss subject matter experts will be available for timely clarifications and reviews

The actual scope of code refactoring will be determined during Phase 1 Discovery

Current safety requirements documentation is complete and accurate

Existing codebase is available and accessible for analysis

Tool licenses (Vector Cast, PC-LINT) costs will be passed through to Client

Project start date is dependent on completion of Client responsibilities and hardware delivery

## Methodology or Approach

CFeynmanCompany will implement a three-phase approach utilizing our blended-shore delivery model:

Phase 1 - Discovery and Gap Analysis (Paid Discovery)

This critical de-risking phase will be executed on a Time & Materials basis to analyze the existing codebase, define the actual scope of refactoring required, and deliver immediate value through DBC file resolution. Activities include code architecture analysis, requirements gap assessment, root cause analysis of DYNO CAN issues, delivery of consolidated DBC files, and detailed scope definition for subsequent phases.

Phase 2 - Safety Requirements Implementation (Indicative)

Based on Phase 1 findings, implement the remaining safety requirements, perform necessary code refactoring, and create comprehensive design documentation. This phase scope and pricing will be formally defined through the output of Phase 1 and may require a Change Order if scope exceeds current estimates.

Phase 3 - Verification and Validation (Indicative)

Execute comprehensive V&V activities including unit testing, static code analysis, bench-level testing, and HIL testing with fault insertion. Deliver complete Software Verification & Validation Report demonstrating ISO 26262 compliance. This phase scope and pricing will be formally defined through the output of Phase 1.

## Acceptance Criteria

The following conditions must be met for acceptance by the Client:

All deliverables meet the technical specifications and quality standards defined in the respective phase

Code coverage metrics (Statement, Branch, MC/DC) achieve the thresholds specified in the safety plan

Static code analysis demonstrates MISRA compliance with acceptable deviation records

Unit tests, integration tests, and HIL tests pass with results documented in the V&V report

Design documentation is complete, accurate, and suitable for safety lifecycle evidence

DBC files resolve data acquisition issues and function correctly in DYNO environment

Deliverables are subject to Client review and will be deemed accepted if no written objections are received within 15 calendar days of submission

All deliverables comply with ISO 26262-6 requirements and Danfoss quality standards

# Assets/Information Required

The following assets, information, and tools are required from the Client to complete the project:

Two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at Client expense

Configured development laptop with all necessary development tools and environment setup

Uninterrupted remote access to stable, pre-configured HIL system for testing activities

Complete source code repository access for existing safety CPU firmware

Current safety requirements documentation and Technical Safety Concept (TSC) Architecture

Existing CAN database files and data acquisition system documentation

Access to Danfoss subject matter experts for clarifications and technical reviews

Tool licenses for Vector Cast and PC-LINT (costs to be passed through to Client)

Safety plan documentation including code coverage requirements and thresholds

DYNO test environment access and configuration details

Project-specific coding standards and guidelines

Access to quality management and review processes for deliverable validation

# Governance and Review

This section addresses the governance and review applied towards the completion of this project including status meetings, milestone reviews, and change management processes.

Weekly status meetings between CFeynmanCompany project team and Danfoss stakeholders

Phase gate reviews at completion of each project phase requiring formal sign-off

Deliverable reviews with 15-day acceptance window for Client feedback

Monthly budget and timeline reviews with early warning at 80% budget utilization

Escalation procedures for technical issues requiring subject matter expert input

Change management process triggered when scope variations are identified

Quality gate reviews for all safety-critical deliverables

Regular code review sessions with Danfoss technical team

Risk assessment reviews at key project milestones

# Out of Scope

The following items are explicitly NOT included in this engagement scope and would require a Change Order if needed:

Hardware design or modification of inverter module components

Development environment setup and configuration on Client systems

Training of Danfoss personnel on developed software or processes

Long-term maintenance or support of delivered software beyond project completion

Integration with systems outside the scope of the safety CPU firmware

Certification or assessment activities beyond ISO 26262 compliance verification

Development of new safety requirements beyond the existing 110 identified requirements

Hardware procurement or logistics management

Creation of new test equipment or modification of existing HIL/DYNO systems

Project management of Client-side activities or resources

Any scope additions identified during Phase 1 that exceed current estimates

# Deliverables

This SOW describes the support needs relating to the project in terms of the following deliverables:

Consolidated DBC File(s) - Optimized CAN database files for DYNO data acquisition system (electronic submission via secure file transfer)

Code Analysis Report - Comprehensive analysis of existing codebase with refactoring scope definition (electronic submission)

Software Design Document - High-level and low-level design documentation for safety software (electronic submission)

Refactored Safety Software - Complete, reviewed, and tested source code for implemented safety functions (electronic submission via repository)

Software Verification & Validation Report - Detailed report containing static analysis, unit test results, code coverage metrics, integration test results, and HIL testing validation (electronic submission)

Unit Test Suite - Complete set of unit tests with documentation (electronic submission)

Test Results Documentation - Comprehensive test execution results and evidence (electronic submission)

Phase Completion Reports - Formal reports at the end of each project phase (electronic submission)

# Project Schedule

The project schedule is structured in three phases with the following estimated timeline:

Project Start Date

Target project start date is September 4, 2025, contingent upon completion of client responsibilities including hardware delivery and system access provisioning.

Phases and Milestones

Phase 1 - Discovery and Gap Analysis: 4-6 weeks from project start

Phase 2 - Safety Requirements Implementation: Duration to be determined based on Phase 1 findings

Phase 3 - Verification and Validation: Duration to be determined based on Phase 1 findings

Estimated Completion Date

Overall project completion is estimated for Q1 2026, pending scope definition from Phase 1 results. Detailed timeline for Phases 2 and 3 will be provided upon completion of the Discovery phase.

# Proposed Team and Organization

CFeynmanCompany will deploy a blended-shore team leveraging our India Design Center for cost-effective delivery and US-based expertise for functional safety oversight.

Roles and Responsibilities

| Role | Classification | Location | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Core | US/India | Overall project coordination, client communication, risk management |
| Functional Safety Consultant | Core | US | ISO 26262 guidance, safety architecture review, compliance oversight |
| Senior Embedded Engineer | Core | India | Requirements implementation, code refactoring, technical leadership |
| Test Engineer | Core | India | Unit testing, integration testing, HIL test execution |
| Software Quality Engineer | Support | India | Static code analysis, code reviews, documentation |
| Technical Lead | Core | India | Technical coordination, architecture guidance, code review |

RASCI Matrix

RASCI Key: R = Responsible, A = Accountable, S = Supporting, C = Consulted, I = Informed

| Activity | Project Manager | Functional Safety Consultant | Senior Embedded Engineer | Test Engineer | Software Quality Engineer | Technical Lead |
| --- | --- | --- | --- | --- | --- | --- |
| Project Planning | R | A | S | S | I | S |
| Requirements Implementation | I | C | A | S | S | R |
| Code Review | I | R | S | S | A | R |
| Testing Activities | I | C | S | A | S | R |
| Documentation | I | C | S | S | A | S |
| Client Communication | A | R | I | I | I | I |
| Quality Assurance | I | R | S | S | A | S |

# Data Retention

Project data including source code, documentation, test results, and communications will be retained on CFeynmanCompany's secure systems for the duration of the project and 24 months after completion. Data will be stored in accordance with CFeynmanCompany's information security policies and applicable data protection regulations. Danfoss will have access to all project data throughout the engagement and will receive complete data transfer upon project completion. CFeynmanCompany will securely delete all project data after the retention period unless otherwise agreed in writing with the Client.

# Risk Management

The following risk management plan addresses key project risks and mitigation strategies:

| Risk | Probability | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- |
| Scope Definition Risk | High | Phase 1 Discovery approach with formal scope definition | Paid discovery phase to analyze and define actual requirements |
| Hardware Delivery Delays | Medium | Clear client responsibilities and timeline dependencies | Alternative development approach using simulation until hardware available |
| Remote Access Issues | Medium | Backup communication channels and escalation procedures | Local development environment setup as contingency |
| Tool License Costs | Low | Pass-through pricing model clearly defined in SOW | Client pre-approval of tool requirements |
| Resource Availability | Medium | Blended-shore model with backup resources | Cross-training and resource pool management |

# Change Management

Changes to the scope of work will be managed through a formal change management process. CFeynmanCompany will trigger the Change Order process when project scope variations are identified or when budget utilization reaches 80% of the estimated amount. All changes must be documented, reviewed, and approved by both parties before implementation. The change management process includes impact assessment, cost estimation, timeline adjustment, and formal approval documentation. No work will proceed on changed scope until written approval is received.

# Project Pricing

This project will be executed on a Time & Materials basis to provide flexibility for the evolving requirements and scope definition through the Discovery phase.

Pricing Structure

| Job Title | Description | Hourly Rate (USD) |
| --- | --- | --- |
| Project Manager | Overall project coordination and client management | $180 |
| Functional Safety Consultant | ISO 26262 expertise and compliance oversight | $220 |
| Senior Embedded Engineer | Requirements implementation and code development | $160 |
| Test Engineer | Testing activities and validation | $140 |
| Software Quality Engineer | Code analysis and quality assurance | $130 |
| Technical Lead | Technical coordination and architecture | $170 |

Additional Pricing

Tool licenses including Vector Cast and PC-LINT are the Client's financial responsibility. CFeynmanCompany can procure these tools on behalf of the Client with costs passed through at actual cost plus applicable taxes.

Payment Schedule

Invoicing will be conducted monthly based on actual hours worked. Payment terms are Net 30 days from invoice date.

Pricing Assumptions

Estimated total project budget is $350,000 - $450,000 USD for all three phases, subject to scope definition in Phase 1. Change Order process will be triggered at 80% of agreed budget amount. Rates are valid for 12 months from SOW effective date.

# Project Assumptions and Client Responsibilities

Project Assumptions

All safety requirements documentation is complete and accurate

Existing codebase is accessible and compilable

HIL and DYNO systems are stable and operational

Standard CFeynmanCompany development processes and tools will be used

Work will be performed during standard business hours with overlap for US/India coordination

Phase 2 and 3 scope will be defined based on Phase 1 Discovery results

No major architectural changes beyond defined refactoring scope

Client Responsibilities

Provide two complete hardware kits with harnesses shipped to CFeynmanCompany India Design Center at Client expense

Ensure uninterrupted remote access to stable, pre-configured HIL system throughout project duration

Provide configured development laptop ready for immediate use

Make subject matter experts available for timely clarifications and technical reviews

Provide complete access to source code repositories and development environments

Supply all required documentation including safety requirements and TSC architecture

Approve tool license purchases and cover associated costs

Respond to deliverable reviews within agreed timeframes

Participate in regular project meetings and milestone reviews

Provide escalation support for technical and administrative issues

# Contact Information

| CFeynmanCompany Contact | Role | Phone | Email |
| --- | --- | --- | --- |
| Praveen | Manager | +1 9234567892 | praveen@cfeynman.com |
| TBD | Project Manager | TBD | TBD |
| TBD | Functional Safety Consultant | TBD | TBD |
| Client Contact | Role | Phone | Email |
| Peter Parker | Head of Procurement | +1 9234567892 | spiderman@danfoss.com |
| TBD | Technical Lead | TBD | TBD |
| TBD | Project Sponsor | TBD | TBD |