# Statement of Work

Template for United States of America
Fixed-Price Standalone SOW

11/Jul/2025

Presented By:

Praveen, Manager

Technical Manager

7301 Parkway Drive, Hanover, MD 21076

+1 9234567892

praveen@cfeynman.com

Revision Table

| Revision | Date | Description of Change |
| --- | --- | --- |
| 1.0 | XXXXX | Initial Release |

Confidentiality Statement

This document contains information that is privileged, confidential, and otherwise protected from disclosure to anyone other than intended recipient(s). As a result, this information should not be disclosed, duplicated or used for any other purpose than to evaluate Actalent. On signing the contract as a result of the process initialized by submission of this document, any right to disclose, duplicate or use the data contained within this document will be to the extent provided in the resulting agreement

Table of Contents

1	Introduction	3

2	Executive Summary	3

3	Scope of Work	3

3.1	Project Requirements	4

3.2	Assumptions	4

3.3	Methodology or Approach	5

3.4	Engineering System Design	5

3.5	Bill of Materials	5

3.6	Acceptance Criteria	6

4	Assets/Information Required	6

5	Governance and Review	7

6	Out of Scope	7

7	Deliverables	8

8	Project Schedule	8

9	Proposed Team and Organization	8

9.1	Roles and Responsibilities	9

9.2	RASCI Matrix	9

10	Data Retention	9

11	Risk Management	10

12	Change Management	10

13	Project Pricing	10

13.1	Pricing Table	11

13.2	Estimated Budget	11

13.3	Payment Terms	11

14	Project Assumptions and Client Responsibilities	11

15	Contact Information	12

Table of Exhibits

Exhibit A – Change Order	27

# Introduction

This Statement of Work (SOW) dated the 11th day of July, 2025 (the "Effective Date") is made and entered into by and between Danfoss, a global engineering solutions corporation, having a place of business at New Jersey, United States (the "Client") and CFeynmanCompany Services, LLC, a Maryland limited liability company, having its principal place of business at 7301 Parkway Drive, Hanover, MD 21076 ("CFeynmanCompany"); individually referenced here after as "Party" and collectively referenced hereafter as the "Parties".

# Executive Summary

Danfoss is developing advanced firmware for a safety-critical inverter module and requires specialized support to complete the functional safety software development lifecycle in compliance with ISO 26262 standards. The project encompasses two critical workstreams: (1) implementation, verification, and validation of approximately 110 remaining safety software requirements with comprehensive testing and documentation, and (2) resolution of critical CAN database (DBC) file issues that are blocking their DYNO test environment data acquisition pipeline.

CFeynmanCompany proposes a three-phase Time & Materials engagement leveraging our blended-shore delivery model. Our India Design Center will execute the bulk of the verification and validation work under the guidance of our US-based functional safety consultant, providing cost-effective expertise while maintaining the highest quality standards. The engagement will operate as an extended team model with dedicated resources, combining onsite coordination, offshore development, and hybrid testing across both remote HIL systems and physical bench setups.

The project will be managed through a structured governance process with regular milestone reviews and a formal change management process triggered at 80% budget utilization. Our US-based project management will ensure seamless coordination with Danfoss stakeholders, while our specialized team will deliver immediate value through a paid discovery phase that includes a quick-win DBC fix, followed by comprehensive implementation and validation phases tailored to the specific requirements identified during discovery.

# Scope of Work

This section lists the project requirements that must be met and describes these requirements as CFeynmanCompany understands them. The project is structured in three phases to manage risk and ensure proper scope definition before committing to fixed deliverables.

## Project Requirements

This subsection lists all the Client project requirements as understood by CFeynmanCompany:

Workstream 1: Functional Safety Software - Implement approximately 110 remaining safety software requirements in compliance with ISO 26262-6 standard

Code refactoring to align existing codebase with Danfoss specified TSC (Technical Safety Concept) Architecture

Development of comprehensive architectural and detailed design documentation for safety lifecycle evidence

Unit testing development and execution to achieve required code coverage metrics (Statement, Branch, MC/DC)

Bench-level integration and requirement-based testing on physical hardware setup

Remote HIL testing including fault insertion tests to validate safety mechanism effectiveness

Workstream 2: DYNO CAN Issues - Root cause analysis of data acquisition failures related to CAN translation

DBC file consolidation, update, and rationalization into master DBC files compatible with DYNO data acquisition module

## Assumptions

This subsection describes assumptions identified for the completion of this project:

The actual scope of code refactoring will be determined during Phase 1 discovery and may require scope adjustment

Root cause of DYNO CAN DBC issues is limited to file format and translation compatibility

Danfoss will provide timely access to subject matter experts for clarifications and approvals

Hardware kits and HIL system access will be available as specified in client responsibilities

Tool licenses (Vector Cast, PC-LINT) will be procured separately as pass-through costs

Project timeline estimates are based on current understanding and may be refined after Phase 1 discovery

## Methodology or Approach

CFeynmanCompany will implement a three-phase approach to manage project risk and ensure proper scope definition:

**Phase 1 - Paid Discovery and Gap Analysis:** This phase will be executed on a Time & Materials basis to analyze the existing codebase, define the actual scope of refactoring work, and deliver an immediate quick-win by resolving the DBC file issues. This phase includes comprehensive code review, architecture analysis, and detailed scope definition for subsequent phases.

**Phase 2 - Implementation and Development:** Based on Phase 1 findings, this phase will focus on implementing the safety requirements, performing code refactoring, and developing comprehensive design documentation. The scope and timeline for this phase will be formally defined by Phase 1 outputs.

**Phase 3 - Verification and Validation:** This phase encompasses comprehensive testing including unit testing, bench-level testing, and HIL testing with fault insertion validation. All testing will be performed to achieve the required coverage metrics and compliance with ISO 26262 standards.

**Note:** Phases 2 and 3 scope and timeline are indicative only and will be formally defined through a Change Order process based on Phase 1 discoveries and client requirements.

## Engineering System Design

The system design encompasses the Safety CPU firmware architecture, CAN communication interfaces, and testing environments. Key components include the inverter module safety functions, CAN database translation layer, DYNO test environment, and HIL validation systems. The architecture will be documented in detail during Phase 1 and refined throughout the implementation phases.

## Bill of Materials

The following software tools and licenses will be required for project execution. These are ballpark estimates based on the issue date and may be subject to change due to vendor cost increases:

Vector Cast licenses for unit testing and coverage analysis (estimated $15,000-20,000 annually)

PC-LINT licenses for static code analysis (estimated $2,000-3,000 per license)

Vector CANoe/CANalyzer licenses for CAN analysis (if not provided by client)

Additional development tools as identified during Phase 1 discovery

**Important Note:** All tool costs are the client's financial responsibility and will be passed through on invoices. CFeynmanCompany can procure these tools on behalf of the client for project convenience.

## Acceptance Criteria

This section identifies and describes the conditions that must be met for acceptance by the Client:

All deliverables must comply with ISO 26262-6 requirements and pass Danfoss internal quality review processes

Code coverage metrics must meet or exceed requirements specified in the safety plan (Statement, Branch, MC/DC)

All unit tests must pass with documented evidence of test execution and results

HIL testing must demonstrate successful fault insertion and safety mechanism validation

Documentation must be complete, reviewed, and approved by designated Danfoss technical reviewers

Deliverables are subject to a 15 calendar day review period; if no written objections are received within this timeframe, deliverables will be deemed accepted

All source code must compile without errors and integrate successfully with existing Danfoss systems

# Assets/Information Required

This section identifies and describes the required assets, information, and tools required from the Client to complete the project:

Hardware: Two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at client expense

Remote Access: Uninterrupted access to a stable, pre-configured HIL system for testing and validation

Development Environment: A configured laptop ready for development work, eliminating setup time from billable hours

Technical Documentation: Complete existing codebase, architecture documents, safety requirements, and TSC specifications

CAN Database Files: All existing DBC files and DYNO system specifications for analysis and optimization

Subject Matter Expert Access: Timely availability of Danfoss technical experts for clarifications, reviews, and approvals

Network Access: Secure VPN access to necessary Danfoss systems and repositories

Testing Environment Access: Access to bench-level testing facilities and DYNO test environment

Approval Authority: Designated reviewers with authority to approve deliverables within the 15-day acceptance window

# Governance and Review

This section addresses the governance and review applied towards the completion of this project including regular status meetings, milestone reviews, and change management processes:

Weekly status meetings between CFeynmanCompany project team and Danfoss stakeholders

Bi-weekly milestone reviews to assess progress against project timeline and deliverables

Monthly executive briefings to senior management at both organizations

Formal change management process triggered when project reaches 80% of estimated budget

15-day deliverable review and acceptance process with escalation procedures for delays

Quality gates at the end of each phase requiring formal approval before proceeding

Risk review meetings scheduled monthly or as needed based on project risk assessment

# Out of Scope

This section states the agreed upon requirements and/or items not included in the Scope of Work. These items would require a significant effort that would impact and require additional work through a Change Order:

Hardware design or modification of the inverter module hardware components

Development of new safety requirements beyond the specified 110 requirements

Integration with systems outside the specified Safety CPU and CAN communication scope

Procurement, installation, or maintenance of development tools and licenses

Training of Danfoss personnel on developed software or processes

Production deployment, manufacturing support, or field service activities

Modification of existing Danfoss HIL or DYNO hardware configurations

Development of graphical user interfaces or operator panels

Compliance with standards other than ISO 26262 (e.g., IEC 61508, EN 50128)

Long-term maintenance or support beyond project completion

# Deliverables

This SOW describes the support needs relating to the project in terms of the following deliverables:

Consolidated DBC File(s) - Optimized CAN database files compatible with DYNO data acquisition system (Electronic delivery via secure file transfer)

Software Design Document - Comprehensive high-level and low-level design documentation for safety software (Electronic delivery via secure file transfer)

Refactored Safety Software - Complete, reviewed, and tested source code for implemented safety functions (Electronic delivery via secure file transfer)

Software Verification & Validation Report - Detailed report containing static code analysis, unit test results, coverage metrics, integration test results, and HIL testing validation (Electronic delivery via secure file transfer)

Phase 1 Discovery Report - Comprehensive analysis of existing code, scope definition for subsequent phases, and recommendations (Electronic delivery via secure file transfer)

Unit Test Suite - Complete unit test framework with automated test execution capability (Electronic delivery via secure file transfer)

Integration Test Documentation - Test procedures, test cases, and execution results for bench-level testing (Electronic delivery via secure file transfer)

# Project Schedule

This section describes the project schedule, including the start date and estimated completion date:

**Project Start Date:** September 4, 2025 (Target kick-off date as specified in RFP)

**Phase 1 - Discovery and Gap Analysis:** 4-6 weeks from project start date

**Phase 2 - Implementation:** Timeline to be determined based on Phase 1 findings (estimated 12-16 weeks)

**Phase 3 - Verification and Validation:** Timeline to be determined based on Phase 1 findings (estimated 8-12 weeks)

**Estimated Project Completion:** March 2026 (subject to Phase 1 scope definition and client dependencies)

# Proposed Team and Organization

This section describes the proposed CFeynmanCompany team and organization, leveraging our blended-shore delivery model with US-based management and functional safety expertise combined with India Design Center execution capabilities.

## Roles and Responsibilities

| Role | Classification | Location | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Core | US (Maryland) | Overall project coordination, client communication, deliverable management |
| Functional Safety Consultant | Core | US (Maryland) | ISO 26262 guidance, safety requirement review, compliance oversight |
| Technical Lead | Core | India Design Center | Architecture design, code review, technical solution guidance |
| Senior Embedded Engineers (2) | Core | India Design Center | Safety software implementation, code refactoring, unit testing |
| V&V Engineers (2) | Core | India Design Center | Test development, HIL testing, coverage analysis, validation reporting |
| CAN/DBC Specialist | Support | India Design Center | CAN database analysis and optimization, DYNO integration |
| Quality Assurance Engineer | Support | India Design Center | Code quality review, documentation review, compliance verification |

## RASCI Matrix

**RASCI Key:** R = Responsible, A = Accountable, S = Supporting, C = Consulted, I = Informed

| Project Activity | Project Manager | Functional Safety Consultant | Technical Lead | Senior Engineers | V&V Engineers | CAN Specialist | QA Engineer |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | A | S | R | S | S | I | I |
| Requirements Analysis | I | A | R | R | S | S | C |
| Code Implementation | I | C | S | A | I | I | S |
| Code Review | S | A | R | S | S | I | R |
| Unit Testing | I | C | S | R | A | I | S |
| HIL Testing | S | A | I | S | R | S | S |
| Documentation Review | A | C | S | S | S | I | R |
| Client Communication | A | S | I | I | I | I | I |
| Deliverable Approval | A | C | I | I | I | I | S |

# Data Retention

Project data including source code, documentation, test results, and communications will be retained on CFeynmanCompany's secure systems for the duration of the project and 24 months after project completion. Data will be stored in encrypted repositories with access limited to authorized project team members and Danfoss designated contacts. All project data will be transferred to Danfoss at project completion, and CFeynmanCompany will maintain backup copies during the retention period for support purposes. Data will be permanently deleted from CFeynmanCompany systems after the retention period unless otherwise agreed in writing.

# Risk Management

This section presents a risk management plan, which includes identifying and evaluating potential risks, assigning ownership, as well as monitoring, and mitigating each:

| Risk | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- |
| Scope Creep | High | Medium | Three-phase approach with formal scope definition in Phase 1 | CFeynmanCompany PM |
| Hardware/HIL Access Delays | Medium | High | Early hardware shipment, backup testing strategies | Danfoss |
| Tool License Delays | Medium | Medium | Early procurement, pass-through cost model | CFeynmanCompany PM |
| SME Availability | Medium | High | Dedicated contact assignments, escalation procedures | Danfoss |
| Code Complexity Higher Than Expected | High | Medium | Discovery phase analysis, change order process | CFeynmanCompany Technical Lead |
| DYNO Integration Issues | Medium | Medium | Quick-win DBC fix in Phase 1, incremental testing | CFeynmanCompany CAN Specialist |

# Change Management

A formal change management process will be triggered when the project reaches 80% of the estimated budget. All changes to scope, timeline, or budget must be documented through a formal Change Order process requiring approval from both parties. Emergency changes may be implemented with verbal approval followed by written confirmation within 48 hours. All changes will be tracked and reported in weekly status meetings with impact assessment on overall project timeline and budget.

# Project Pricing

This project will be executed on a Time & Materials (T&M) basis providing flexibility for evolving requirements and scope adjustments. The pricing structure reflects our blended-shore delivery model with competitive rates for India-based resources and premium rates for US-based expertise.

## Pricing Table

| Job Title | Description | Hourly Rate |
| --- | --- | --- |
| Project Manager | Overall project coordination and client management | $180/hour |
| Functional Safety Consultant | ISO 26262 expertise and compliance guidance | $220/hour |
| Technical Lead | Architecture and technical solution leadership | $95/hour |
| Senior Embedded Engineer | Safety software implementation and code development | $85/hour |
| V&V Engineer | Testing, validation, and verification activities | $80/hour |
| CAN/DBC Specialist | CAN database optimization and DYNO integration | $90/hour |
| Quality Assurance Engineer | Code quality and documentation review | $75/hour |

## Estimated Budget

**Total Estimated Project Budget:** $450,000 - $650,000 (subject to Phase 1 scope definition)

**Additional Pricing:** Tool licenses (Vector Cast, PC-LINT, etc.) will be billed as pass-through costs at actual vendor pricing plus administrative handling fee of 5%.

## Payment Terms

Monthly invoicing based on actual hours worked and expenses incurred. Payment terms: Net 30 days from invoice date. Change Order process will be triggered at 80% of estimated budget burn to ensure continued funding authorization.

# Project Assumptions and Client Responsibilities

**Project Assumptions:**

Project will commence on September 4, 2025 as targeted

Danfoss will provide all required assets and access within 2 weeks of project start

All existing documentation and codebase will be provided in English

Standard business hours overlap between India and US teams will be sufficient for collaboration

No major architectural changes will be required beyond specified refactoring

HIL system will be available and stable for remote testing throughout the project

**Client Responsibilities:**

Provide two complete hardware kits with harnesses shipped to India Design Center at client expense

Ensure uninterrupted remote access to HIL systems throughout project duration

Provide pre-configured development laptop ready for immediate use

Assign dedicated subject matter experts with guaranteed availability for project support

Provide timely review and approval of deliverables within 15-day acceptance window

Maintain secure VPN access and necessary system permissions for CFeynmanCompany team

Procure or approve procurement of required tool licenses (Vector Cast, PC-LINT)

Provide escalation path for issue resolution and decision-making authority

# Contact Information

| Name | Role | Phone | Email |
| --- | --- | --- | --- |
| Praveen, Manager | Technical Manager | +1 9234567892 | praveen@cfeynman.com |
| Enter Client PM Name | Project Manager | TBD | TBD |
| Enter Client Technical Lead | Technical Lead | TBD | TBD |