# Statement of Work

Template for United States of America
Time & Material SOW

19/Jul/2025

Presented By:

Praveen

Manager

7301 Parkway Drive, Hanover, MD 21076

+1 9234567892

pravenn@cfeynman.com

Revision Table

| Revision | Date | Description of Change |
| --- | --- | --- |
| 1.0 | XXXXX | Initial Release |

Confidentiality Statement

This document contains information that is privileged, confidential, and otherwise protected from disclosure to anyone other than intended recipient(s). As a result, this information should not be disclosed, duplicated or used for any other purpose than to evaluate Actalent. On signing the contract as a result of the process initialized by submission of this document, any right to disclose, duplicate or use the data contained within this document will be to the extent provided in the resulting agreement

Table of Contents

1	Introduction	2

2	Executive Summary	2

3	Scope of Work	2

3.1	Project Requirements	2

3.2	Assumptions	3

3.3	Methodology or Approach	3

3.4	Acceptance Criteria	4

4	Assets/Information Required	5

5	Governance and Review	5

6	Out of Scope	6

7	Deliverables	6

8	Project Schedule	7

9	Proposed Team and Organization	8

10	Data Retention	8

11	Risk Management	9

12	Change Management	9

13	Project Pricing	10

14	Project Assumptions and Client Responsibilities	11

15	Contact Information	12

Table of Exhibits

Exhibit A – Change Order	27

# Introduction

This Statement of Work (SOW) dated the 19th day of July, 2025 (the "Effective Date") is made and entered into by and between Kimi, a corporation, having a place of business at New Jersey, United States (the "Client") and CFeynmanCompany Services, LLC, a Maryland limited liability company, having its principal place of business at 7301 Parkway Drive, Hanover, MD 21076 ("CFeynmanCompany"); individually referenced here after as "Party" and collectively referenced hereafter as the "Parties".

# Executive Summary

Kimi is developing advanced firmware for a safety-critical inverter module and requires specialized support to complete the functional safety software implementation, verification, and validation (V&V) in accordance with ISO 26262-6 standards. The client faces two critical challenges: completing approximately 110 remaining safety software requirements with rigorous V&V processes that are tying up their core team, and resolving critical CAN database (DBC) file issues that are blocking their DYNO test environment data acquisition capabilities.

CFeynmanCompany proposes a comprehensive solution leveraging our blended-shore model with our India Design Center for the bulk of the V&V work and our US-based consultant for high-value functional safety guidance. The engagement will be delivered through a structured three-phase approach on a Time and Materials (T&M) basis, beginning with a paid discovery phase to properly define scope and deliver immediate value through DBC file resolution, followed by implementation and validation phases.

The project will be managed through regular milestone reviews and governance processes, with our team acting as an extension of Kimi's internal team. Our approach includes dedicated project management coordination, escalation procedures, and comprehensive documentation to ensure ISO 26262 compliance while maintaining project velocity and client satisfaction.

# Scope of Work

This section lists the project requirements that must be met and describes these requirements as CFeynmanCompany understands them. The scope is structured in three phases to manage risk and ensure proper definition of work requirements.

## Project Requirements

This subsection lists all the Client project requirements as understood by CFeynmanCompany:

Implementation of approximately 110 remaining safety software requirements in accordance with ISO 26262-6 standard

Code refactoring of existing codebase to align with Kimi specified TSC (Technical Safety Concept) Architecture

Creation of comprehensive architectural and detailed design documents serving as evidence for the safety lifecycle

Development and execution of unit tests to achieve required code coverage metrics (Statement, Branch, MC/DC)

Performance of bench-level integration and requirement-based testing on physical bench setup

Execution of remote HIL testing including fault insertion tests to validate safety mechanism effectiveness

Resolution of critical DYNO CAN database (DBC) file issues causing data acquisition failures

Investigation of root cause analysis for CAN translation failures

Consolidation and optimization of multiple existing DBC files into master DBCs compatible with DYNO data acquisition module

## Assumptions

This subsection describes assumptions identified for the completion of this project:

Client will provide two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at client's expense

Client will provide uninterrupted remote access to a stable, pre-configured HIL system

Client will provide a configured laptop ready for development work to minimize setup time

Client's subject matter experts (SMEs) will be available for timely clarifications and reviews

Existing codebase and documentation will be made available at project start

The scope of code refactoring requirements will be fully defined during Phase 1 Discovery

All required development tools and licenses will be available or procured as needed

Project timeline assumes standard business day availability and response times from client team

Safety plan and TSC Architecture documentation will be provided by client

## Methodology or Approach

CFeynmanCompany will implement a three-phase approach designed to de-risk the project and ensure all requirements are properly addressed:

Phase 1: Paid Discovery and Gap Analysis (4-6 weeks)

Comprehensive analysis of existing codebase and architecture

Root cause analysis and immediate resolution of DBC file issues for DYNO system

Detailed assessment of the 110 safety requirements and refactoring scope

Gap analysis between current state and ISO 26262-6 compliance requirements

Definition of detailed work breakdown structure for subsequent phases

Delivery of functional DBC files as immediate project value

Creation of detailed project plan and resource estimates for Phases 2 and 3

Phase 2: Safety Software Implementation and Refactoring (Indicative: 12-16 weeks)

Implementation of remaining 110 safety software requirements

Code refactoring to align with TSC Architecture specifications

Creation of comprehensive design documentation

Development of unit test framework and test cases

Static code analysis and MISRA compliance verification

Integration testing preparation and execution

Phase 3: Verification and Validation (Indicative: 8-12 weeks)

Execution of comprehensive unit testing with code coverage analysis

Bench-level testing and requirement-based testing

Remote HIL testing including fault insertion validation

Safety mechanism effectiveness validation

Final verification and validation report preparation

ISO 26262 compliance documentation and evidence package

Important Note: The scope and timeline for Phases 2 and 3 are indicative only and will be formally defined based on the findings and recommendations from Phase 1. Any changes to scope will be managed through the formal Change Order process.

## Acceptance Criteria

This section identifies and describes the conditions that must be met for acceptance by the Client:

All deliverables must meet the specifications and requirements defined in each project phase

Software deliverables must pass all defined unit tests with required code coverage metrics (Statement, Branch, MC/DC)

DBC files must successfully enable data acquisition in the DYNO test environment

All documentation must be complete, accurate, and comply with ISO 26262-6 evidence requirements

HIL testing must demonstrate successful fault insertion and safety mechanism validation

Static code analysis must show compliance with agreed-upon coding standards (MISRA)

All deliverables are subject to Client review and will be deemed accepted if no written objections are received within 15 calendar days of delivery

Acceptance criteria for each phase will be defined at the completion of Phase 1 based on detailed requirements analysis

# Assets/Information Required

This section identifies and describes the required assets, information, and tools required from the Client to complete the project:

- Hardware Provision: Two complete hardware kits with harnesses, shipped to CFeynmanCompany India Design Center at Client expense, to be provided within 2 weeks of project start

- Remote System Access: Uninterrupted access to stable, pre-configured HIL system with appropriate security credentials and VPN access

- Development Environment: One configured laptop with all necessary development tools, compilers, and software installed and ready for immediate use

- Documentation Package: Complete existing codebase, TSC Architecture documentation, safety plan, existing DBC files, and all relevant technical specifications

- Subject Matter Expert Access: Dedicated SME availability for technical clarifications with committed response time of 48 hours for critical issues

- Testing Environment Access: Access to DYNO test system for validation and DBC file verification

- Tool Licenses: Access to or provision of required development and testing tools including Vector CANoe/CANalyzer, VectorCAST, PC-LINT, and other ISO 26262 compliant tools

- Quality and Compliance Documentation: Current safety requirements documentation, coding standards, and compliance checklists

- Project Infrastructure: Access to version control systems, bug tracking systems, and project management tools used by Client team

# Governance and Review

This section addresses the governance and review applied towards the completion of this project including project management, milestone reviews, and quality assurance processes:

Weekly status meetings via video conference to review progress, address issues, and coordinate activities

Phase gate reviews at the completion of each project phase with formal go/no-go decision points

Bi-weekly deliverable reviews with structured feedback and approval processes

Monthly executive summary reports to key stakeholders on both client and CFeynmanCompany sides

Escalation procedures for technical and project management issues with defined response times

Quality gate reviews for all major deliverables before client submission

Regular risk assessment and mitigation planning sessions

Change control board meetings as needed to evaluate and approve scope changes

Final phase acceptance meetings with formal sign-off procedures

# Out of Scope

This section states the agreed upon requirements and/or items not included in the Scope of Work. These items would require additional work and a Change Order if needed:

Hardware design or modification of existing hardware components

Development of new safety requirements beyond the identified 110 requirements

Certification activities or direct interaction with certification bodies

Production-ready software deployment or manufacturing support

Training of Client personnel on developed software or processes

Long-term maintenance or support beyond project completion

Integration with systems outside the scope of the inverter module firmware

Development of test automation frameworks beyond unit testing

Creation or modification of HIL test benches or DYNO hardware systems

Patent analysis or intellectual property assessments

Regulatory compliance documentation beyond ISO 26262-6 software requirements

Project management of Client internal activities or parallel workstreams

# Deliverables

This SOW describes the support needs relating to the project in terms of the following deliverables:

- Phase 1 Discovery Report: Comprehensive analysis document including gap analysis, root cause analysis of DBC issues, and detailed project plan for subsequent phases (electronic delivery via secure file transfer)

- Consolidated DBC Files: Fully functional and optimized DBC files for DYNO data acquisition system (electronic delivery via secure file transfer)

- Software Design Document: Comprehensive architectural and detailed design documentation for safety software (electronic delivery via secure file transfer)

- Refactored Safety Software: Complete, reviewed, and tested source code for implemented safety functions with version control documentation (electronic delivery via secure file transfer)

- Unit Test Suite: Complete unit test framework, test cases, and automated test execution scripts (electronic delivery via secure file transfer)

- Verification and Validation Report: Detailed report containing static code analysis results, unit test results with code coverage metrics, integration test results, and HIL testing results including fault insertion validation (electronic delivery via secure file transfer)

- ISO 26262 Compliance Package: Complete documentation package serving as evidence for ISO 26262-6 compliance including traceability matrices and safety case documentation (electronic delivery via secure file transfer)

- Project Closeout Report: Final project summary including lessons learned, recommendations, and knowledge transfer documentation (electronic delivery via secure file transfer)

# Project Schedule

This section describes the project schedule, including the start date and estimated completion dates for each phase:

Project Start Date

Target project start date is September 4, 2025, subject to completion of contract execution and receipt of required client assets and access credentials.

Estimated Completion Dates

Phase 1 (Discovery): Completion by October 16, 2025 (4-6 weeks from start)

Phase 2 (Implementation): Completion by February 10, 2026 (12-16 weeks, indicative)

Phase 3 (V&V): Completion by May 5, 2026 (8-12 weeks, indicative)

Overall Project Completion: May 5, 2026 (approximately 8-9 months total duration)

Note: Phase 2 and 3 timelines are indicative and will be refined based on Phase 1 findings. All dates assume standard business day availability and timely client responses for reviews and approvals.

# Proposed Team and Organization

This section describes the proposed CFeynmanCompany team and organization, leveraging our blended-shore model with our India Design Center and US-based expertise:

Roles and Responsibilities

| Role | Classification | Location | Responsibilities |
| --- | --- | --- | --- |
| Project Manager | Core | US/India | Overall project coordination, client communication, resource management, risk mitigation |
| Functional Safety Consultant | Core | US | ISO 26262 expertise, safety architecture review, compliance guidance |
| Lead Software Engineer | Core | India | Technical leadership, code review, architecture design, implementation oversight |
| Senior Software Engineers (2) | Core | India | Safety requirements implementation, code refactoring, unit test development |
| Software Test Engineer | Core | India | Test framework development, HIL testing, V&V execution |
| Quality Assurance Engineer | Support | India | Static code analysis, compliance verification, documentation review |
| Technical Writer | Support | India | Documentation creation, ISO 26262 evidence package preparation |

RASCI Matrix

RASCI Key: R = Responsible, A = Accountable, S = Supporting, C = Consulted, I = Informed

| Activity | Project Manager | Functional Safety Consultant | Lead Software Engineer | Senior Software Engineers | Software Test Engineer | Quality Assurance Engineer | Technical Writer |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | A | C | R | S | I | I | I |
| Requirements Analysis | S | A | R | R | C | I | I |
| Code Implementation | I | C | A | R | S | I | I |
| Testing & V&V | S | C | S | S | A | R | I |
| Documentation | S | C | S | S | S | R | A |
| Quality Assurance | I | A | S | S | S | R | S |
| Client Communication | A | S | C | I | I | I | I |
| Deliverable Review | A | C | R | S | S | S | S |

# Data Retention

This section includes a description of how project data will be retained, managed, and used:

All project data including source code, documentation, test results, and communications will be retained on CFeynmanCompany's secure systems for the duration of the project and 24 months after completion

Project data will be stored using industry-standard security protocols with appropriate access controls and backup procedures

Client will have full access to all project data throughout the engagement and upon request

Upon project completion, all deliverables and project data will be transferred to the Client's designated systems

CFeynmanCompany will permanently delete all client proprietary data from our systems within 30 days of Client's written request, provided all contractual obligations have been fulfilled

Version control history and audit trails will be maintained to support traceability requirements for ISO 26262 compliance

Regular backups will be performed to ensure data integrity and availability throughout the project lifecycle

# Risk Management

This section presents the risk management approach for the project:

| Risk | Probability | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- |
| Scope Definition Risk | High | Phase 1 discovery approach, formal scope validation | Dedicated discovery phase with detailed analysis |
| Resource Availability | Medium | Cross-training, resource pool management | Maintain backup resources, flexible allocation |
| Technical Complexity | Medium | Expert consultation, proof-of-concept validation | Senior technical leadership, US functional safety expertise |
| Client Dependency Delays | High | Clear SLAs, escalation procedures | Formal client responsibilities, regular checkpoint reviews |
| Tool/License Availability | Medium | Early procurement, alternative tool evaluation | Pass-through cost model, early identification |
| HIL System Access | Medium | Backup testing strategies, remote access protocols | Multiple access paths, local testing capabilities |
| Requirement Changes | High | Change control process, impact assessment | Formal change management, 80% budget trigger |

# Change Management

This section describes the change management process for handling scope, schedule, or resource modifications:

- Change Request Initiation: Any party may initiate a change request through formal written notification describing the proposed change, rationale, and expected impact

- Impact Assessment: CFeynmanCompany will conduct a comprehensive impact assessment within 5 business days, covering scope, schedule, cost, and resource implications

- Change Order Preparation: For approved changes, CFeynmanCompany will prepare a detailed Change Order including revised scope, timeline, and pricing

- Client Review and Approval: Client has 10 business days to review and approve or reject the Change Order

- Budget Monitoring: CFeynmanCompany will trigger the Change Order process when project costs reach 80% of the current approved budget

- Implementation: Approved changes will be implemented according to the revised project plan with updated deliverables and milestones

- Documentation: All changes will be formally documented and incorporated into project governance and tracking systems

# Project Pricing

This section details the pricing structure and payment terms for the engagement:

Pricing Model

This engagement will be conducted on a Time and Materials (T&M) basis to provide the flexibility required for a project with evolving requirements and technical unknowns.

Hourly Rates

| Job Title | Description | Hourly Rate (USD) |
| --- | --- | --- |
| Project Manager | Overall project management and client coordination | $165 |
| Functional Safety Consultant | ISO 26262 expertise and compliance guidance | $195 |
| Lead Software Engineer | Technical leadership and architecture design | $135 |
| Senior Software Engineer | Implementation and development work | $115 |
| Software Test Engineer | Testing and validation activities | $105 |
| Quality Assurance Engineer | QA and compliance verification | $95 |
| Technical Writer | Documentation and evidence package preparation | $85 |

Estimated Project Budget

| Phase/Milestone | Target Completion | Estimated Cost |
| --- | --- | --- |
| Phase 1: Discovery and Gap Analysis | October 16, 2025 | $75,000 - $95,000 |
| Phase 2: Implementation (Indicative) | February 10, 2026 | $180,000 - $220,000 |
| Phase 3: V&V (Indicative) | May 5, 2026 | $120,000 - $150,000 |
| Total Project (Estimated) | May 5, 2026 | $375,000 - $465,000 |

Additional Pricing

The following items will be passed through to the Client at cost:

Software tool licenses including VectorCAST, PC-LINT, and other specialized testing tools

Travel expenses if onsite support is required

Hardware or equipment purchases specifically for this project

Third-party training or certification costs if required

Payment Terms

Invoices will be submitted monthly based on actual hours worked and approved expenses. Payment terms are Net 30 days from invoice date.

# Project Assumptions and Client Responsibilities

This section outlines key project assumptions and specific client responsibilities essential for project success:

Project Assumptions

Standard business hours operation (Monday-Friday, 8 AM - 6 PM local time zones)

Client team availability for reviews, approvals, and clarifications within agreed timeframes

Stable and secure remote access to client systems and development environments

Existing codebase is reasonably well-structured and documented

Safety requirements are clearly defined and traceable

HIL and DYNO systems are operational and accessible for testing

No major changes to fundamental system architecture during project execution

Client Responsibilities

- Provide complete hardware kits with harnesses shipped to CFeynmanCompany India Design Center within 2 weeks of project start

- Establish and maintain stable remote access to HIL system with appropriate security credentials

- Supply configured development laptop with all necessary tools and software pre-installed

- Ensure timely availability of subject matter experts for technical clarifications (48-hour response SLA for critical issues)

- Provide complete project documentation including existing codebase, safety requirements, TSC architecture, and coding standards

- Conduct timely reviews and approvals of deliverables within agreed timeframes (15 calendar days for acceptance)

- Maintain operational DYNO and HIL testing environments throughout project duration

- Provide access to version control systems, bug tracking, and project management tools

- Ensure appropriate legal and compliance approvals for offshore development activities

- Support escalation and issue resolution through designated project contacts

# Contact Information

This section provides contact information for key personnel from both organizations:

| Name | Role | Phone | Email |
| --- | --- | --- | --- |
| Praveen | Project Manager | +1 9234567892 | pravenn@cfeynman.com |
| Enter Name | Functional Safety Consultant | Enter Phone | Enter Email |
| Enter Name | Lead Software Engineer | Enter Phone | Enter Email |
| Peter Parker | Head of Procurement | +1 9234567892 | spiderman@kimi.com |
| Enter Name | Project Sponsor | Enter Phone | Enter Email |
| Enter Name | Technical Lead | Enter Phone | Enter Email |